## HS android app revamp
# | Project | Tracker | Status | Priority | Subject | Author | Assignee | Updated | Category | Start date | Created | Description
893586 | HealthSolutions Revamp | Bug | New | Urgent | Getting un expected error in doctor booking | Hamza Zubair | Shaji Ul Haq | 2020-11-03 12:27 PM | Android | 2020-11-03 | 2020-11-03 12:27 PM
893560 | HealthSolutions Revamp | Bug | New | Low | "L" should be in lower case in text "Please pick an image" if the user places order with out uploading prescription image in chemist and diagnostics (Order by prescription) | Hamza Zubair | Shaji Ul Haq | 2020-11-03 09:37 AM |  | 2020-11-03 | 2020-11-03 09:35 AM
893559 | HealthSolutions Revamp | Bug | New | High | Getting un expected error on payment through jazz cash and easy paisa | Hamza Zubair | Shaji Ul Haq | 2020-11-03 09:13 AM | Android | 2020-11-03 | 2020-11-03 09:13 AM | First apply bank discount and go back to payment screen. Select easy paisa or jazz cash and click on "OK" button. An un expected error is coming.
893555 | HealthSolutions Revamp | Bug | New | High | The discounted amount of chemist product is greater than its actual amount | Hamza Zubair | Shaji Ul Haq | 2020-11-03 08:59 AM | Android | 2020-11-03 | 2020-11-03 08:59 AM | See the chemist product, "ABODINE" whose actual price is "Rs. 34.33" and discounted amount is showing as, "Rs. 60" . The discounted amount of any product could not be greater than its actual price.
893553 | HealthSolutions Revamp | Bug | New | High | Actual chemist product price is showing instead of discounted price in Cart screen | Hamza Zubair | Shaji Ul Haq | 2020-11-03 08:53 AM | Android | 2020-11-03 | 2020-11-03 08:53 AM
893551 | HealthSolutions Revamp | Bug | New | High | "Cart empty" toast message is coming on increasing the no of products rapidly in "Place Order" screen | Hamza Zubair | Shaji Ul Haq | 2020-11-03 08:16 AM | Android | 2020-11-03 | 2020-11-03 08:16 AM | Add a blood product, go to cart and increase the product quantity rapidly. At a certain point, a message will come as "Cart empty" and after that "Un expected error" will start coming on every screen.