## Worksheet
# | Project | Tracker | Parent task | Status | Priority | Subject | Author | Assignee | Updated | Category | Sprint/Milestone | Start date | Due date | Estimated time | Total estimated time | Spent time | Total spent time | % Done | Created | Closed | Last updated by | Related issues | Files | Story points | Sequencing | Private | Description
893192 | HealthSolutions Revamp | Bug |  | New | High | There should be an option to add location on sign up | Hamza Zubair | Shaji Ul Haq | 10/29/2020 11:20 | Android |  | 10/29/2020 |  |  |  | 0 | 0 | 0 | 10/29/2020 11:20 | [6 empty] | No
893190 | HealthSolutions Revamp | Bug |  | New | High | Add a logout option in drawer | Hamza Zubair | Shaji Ul Haq | 10/29/2020 11:03 | Android |  | 10/29/2020 |  |  |  | 0 | 0 | 0 | 10/29/2020 11:03 | [6 empty] | No
893189 | HealthSolutions Revamp | Bug |  | New | High | There should be an option to delete individual product from cart screen | Hamza Zubair | Shaji Ul Haq | 10/29/2020 11:00 | Android |  | 10/29/2020 |  |  |  | 0 | 0 | 0 | 10/29/2020 11:00 | [6 empty] | No
893188 | HealthSolutions Revamp | Bug |  | New | High | The blood product quantity is not increasing after 9 in blood request screen | Hamza Zubair | Shaji Ul Haq | 10/29/2020 10:59 | Android |  | 10/29/2020 |  |  |  | 0 | 0 | 0 | 10/29/2020 10:59 | [6 empty] | No
893187 | HealthSolutions Revamp | Bug |  | New | High | Add an option to edit and update profile info and picture | Hamza Zubair | Shaji Ul Haq | 10/29/2020 11:06 | Android |  | 10/29/2020 |  |  |  | 0 | 0 | 0 | 10/29/2020 10:58 |  | Hamza Zubair |  |  |  |  | No
893175 | HealthSolutions Revamp | Bug |  | New | Low | Adjust the last field spacing in appointment details screen | Hamza Zubair | Shaji Ul Haq | 10/29/2020 8:36 | Android |  | 10/29/2020 |  |  |  | 0 | 0 | 0 | 10/29/2020 8:36 | [6 empty] | No
893174 | HealthSolutions Revamp | Bug |  | New | Low | Reduce the size of the calender icon in Appointment details screen | Hamza Zubair | Shaji Ul Haq | 10/29/2020 8:35 | Android |  | 10/29/2020 |  |  |  | 0 | 0 | 0 | 10/29/2020 8:35 | [6 empty] | No
893172 | HealthSolutions Revamp | Bug |  | New | Low | On scrolling down the Doctor's appointment page for reloading, the reloading icon is not removing and keeps rotating | Hamza Zubair | Shaji Ul Haq | 10/29/2020 7:56 | Android |  | 10/29/2020 |  |  |  | 0 | 0 | 0 | 10/29/2020 7:56 | [6 empty] | No
892825 | HealthSolutions Revamp | Feature |  | New | Normal | Add a "Promo code" discount feature in each section. The promo code will not be applied on already discounted products and once promo code is applied than the user should not be able to avail bank discount on that particular products. | Hamza Zubair | Shaji Ul Haq | 10/27/2020 6:39 | Android |  | 10/27/2020 |  |  |  | 0 | 0 | 0 | 10/27/2020 6:39 | [6 empty] | No
892824 | HealthSolutions Revamp | Bug |  | New | Normal | On applying the bank discount individually on multiple products one by one than on second attempt after applying discount, the wrong total amount is displaying on bank discount screen. The added discounted total amount of each product should be displayed. | Hamza Zubair | Shaji Ul Haq | 10/27/2020 6:36 | Android |  | 10/27/2020 |  |  |  | 0 | 0 | 0 | 10/27/2020 6:36 | [6 empty] | No
892820 | HealthSolutions Revamp | Bug |  | Resolved | Urgent | Unable to use wallet through payment methods, if enough amount is available in wallet but still getting "Unsufficient balance" on doing transaction | Hamza Zubair | Shaji Ul Haq | 10/27/2020 6:55 | Android |  | 10/27/2020 |  |  |  | 0 | 0 | 0 | 10/27/2020 6:20 |  | Shaji Ul Haq |  |  |  |  | No
892767 | HealthSolutions Revamp | Feature |  | New | Low | Add history option in drawer | Hamza Zubair | Shaji Ul Haq | 10/26/2020 12:04 | Android |  | 10/26/2020 |  |  |  | 0 | 0 | 0 | 10/26/2020 12:04 | [6 empty] | No
892755 | HealthSolutions Revamp | Bug |  | Resolved | Normal | On clicking on "Unsufficient balance in wallet" dialog box, the app should take the user back to the payment screen instead of home screen to let the user to select any other payment option | Hamza Zubair | Shaji Ul Haq | 10/26/2020 10:34 | Android |  | 10/26/2020 |  |  |  | 0 | 0 | 0 | 10/26/2020 9:24 |  | Shaji Ul Haq |  |  |  |  | No
892753 | HealthSolutions Revamp | Bug |  | New | High | On using phone's back button, the app is taking back user to the previous opened screens but it should not. The previous screens history should be removed | Hamza Zubair | Shaji Ul Haq | 10/26/2020 9:10 | Android |  | 10/26/2020 |  |  |  | 0 | 0 | 0 | 10/26/2020 9:10 | [6 empty] | No
892752 | HealthSolutions Revamp | Bug |  | Closed | Low | Change "Equipments" to "Equipment" in equipment section home screen | Hamza Zubair | Shaji Ul Haq | 10/27/2020 6:04 | Android |  | 10/26/2020 |  |  |  | 0 | 0 | 0 | 10/26/2020 9:06 | 10/27/2020 6:04 | Hamza Zubair |  |  |  |  | No
892751 | HealthSolutions Revamp | Bug |  | Resolved | High | On selecting any payment method in G-segment, credit card web view is opening | Hamza Zubair | Shaji Ul Haq | 10/28/2020 10:18 | Android |  | 10/26/2020 |  |  |  | 0 | 0 | 0 | 10/26/2020 8:57 |  | Shaji Ul Haq |  |  |  |  | No
892749 | HealthSolutions Revamp | Bug |  | New | High | Wrong total amount is showing on bank discount verification screen | Hamza Zubair | Shaji Ul Haq | 10/26/2020 8:38 | Android |  | 10/26/2020 |  |  |  | 0 | 0 | 0 | 10/26/2020 8:38 | [6 empty] | No
892745 | HealthSolutions Revamp | Bug |  | Resolved | Urgent | If there is not enough amount available in wallet than on selecting payment method as wallet on transaction, a message should be displayed as, "No enough amount available in wallet" | Hamza Zubair | Shaji Ul Haq | 10/26/2020 12:17 | Android |  | 10/26/2020 |  |  |  | 0 | 0 | 0 | 10/26/2020 8:10 |  | Shaji Ul Haq |  |  |  |  | No
892478 | HealthSolutions Revamp | Bug |  | Closed | Urgent | Un expected error is coming on uploading high resolution image, completing the form and clicking on "Submit" button. The data is stored in database but the user is not signed up | Hamza Zubair | Shaji Ul Haq | 10/26/2020 7:30 | Android |  | 10/23/2020 |  |  |  | 0 | 0 | 0 | 10/23/2020 15:02 | 10/26/2020 7:30 | Hamza Zubair |  |  |  |  | No
892476 | HealthSolutions Revamp | Bug |  | Closed | High | Display delivery charges in bank discount screen | Hamza Zubair |  | 10/26/2020 8:38 |  |  | 10/23/2020 |  |  |  | 0 | 0 | 0 | 10/23/2020 14:51 | 10/26/2020 8:38 | Hamza Zubair |  |  |  |  | No
892470 | HealthSolutions Revamp | Task |  | Closed | Low | Change "Enter topup amount" to just "Enter Amount" in wallet section | Hamza Zubair | Shaji Ul Haq | 10/23/2020 15:31 | Android |  | 10/23/2020 |  |  |  | 0 | 0 | 0 | 10/23/2020 14:40 | 10/23/2020 15:31 | Shaji Ul Haq |  |  |  |  | No
892469 | HealthSolutions Revamp | Bug |  | Closed | Normal | If there are no points available than "0" should be displayed in "Available Points" inside wallet | Hamza Zubair | Shaji Ul Haq | 10/29/2020 11:16 | Android |  | 10/23/2020 |  |  |  | 0 | 0 | 0 | 10/23/2020 14:39 | 10/29/2020 11:16 | Hamza Zubair |  |  |  |  | No
892464 | HealthSolutions Revamp | Bug |  | Closed | Immediate | Getting an error on wallet top up | Hamza Zubair | Shaji Ul Haq | 10/23/2020 14:41 |  |  | 10/23/2020 |  |  |  | 0 | 0 | 0 | 10/23/2020 13:50 | 10/23/2020 14:41 | Hamza Zubair |  |  |  |  | No
892463 | HealthSolutions Revamp | Bug |  | Resolved | Normal | Unable to complete payment method on going to web view and than going back to payment screen and than selecting any option. In this case add a message that "The cart is now empty. Please order again" | Hamza Zubair |  | 10/26/2020 12:43 |  |  | 10/23/2020 |  |  |  | 0 | 0 | 0 | 10/23/2020 13:43 |  | Shaji Ul Haq |  |  |  |  | No
892396 | HealthSolutions Revamp | Bug |  | Closed | Urgent | The amount Rs. 1 is showin in credit card web view for all the transactions | Hamza Zubair | Shaji Ul Haq | 10/23/2020 14:52 |  |  | 10/23/2020 |  |  |  | 0 | 0 | 0 | 10/23/2020 8:42 | 10/23/2020 14:52 | Hamza Zubair |  |  |  |  | No
892391 | HealthSolutions Revamp | Bug |  | Closed | High | App is crashing on uploading high resolution image on sign up | Hamza Zubair |  | 10/26/2020 8:14 |  |  | 10/23/2020 |  |  |  | 0 | 0 | 0 | 10/23/2020 7:49 | 10/26/2020 8:14 | Hamza Zubair |  |  |  |  | No
892390 | HealthSolutions Revamp | Task |  | Closed | Low | Change the profile pic upload icon on sign up | Hamza Zubair | Shaji Ul Haq | 10/26/2020 8:12 | Android |  | 10/23/2020 |  |  |  | 0 | 0 | 0 | 10/23/2020 7:45 | 10/26/2020 8:12 | Hamza Zubair |  |  |  |  | No
892389 | HealthSolutions Revamp | Bug |  | Closed | High | The theme of the "Place order" screen in "Fitness" and "Home Care" (Order by search) sections is wrong. Change the theme to default app theme i.e red and white | Hamza Zubair | Shaji Ul Haq | 10/26/2020 8:15 | Android |  | 10/23/2020 |  |  |  | 0 | 0 | 0 | 10/23/2020 7:28 | 10/26/2020 8:15 | Hamza Zubair |  |  |  |  | No
892388 | HealthSolutions Revamp | Bug |  | Closed | Urgent | Getting un expected error in Bank discount verification screen | Hamza Zubair | Shaji Ul Haq | 10/26/2020 8:46 | Android |  | 10/23/2020 |  |  |  | 0 | 0 | 0 | 10/23/2020 7:25 | 10/26/2020 8:46 | Hamza Zubair |  |  |  |  | No
892387 | HealthSolutions Revamp | Bug |  | New | Urgent | Getting un expected error on payment with Bank transfer | Hamza Zubair |  | 10/23/2020 7:24 |  |  | 10/23/2020 |  |  |  | 0 | 0 | 0 | 10/23/2020 7:24 | [6 empty] | No
892386 | HealthSolutions Revamp | Task |  | Resolved | High | Lock the landscape mode throgh out the app | Hamza Zubair | Shaji Ul Haq | 10/27/2020 13:00 | Android |  | 10/23/2020 |  |  |  | 0 | 0 | 0 | 10/23/2020 7:15 |  | Shaji Ul Haq |  |  |  |  | No
892385 | HealthSolutions Revamp | Bug |  | New | High | Images not displaying in "Partners" list | Hamza Zubair | Shaji Ul Haq | 10/23/2020 8:40 | Android |  | 10/23/2020 |  |  |  | 0 | 0 | 0 | 10/23/2020 7:09 |  | Shaji Ul Haq |  |  |  |  | No | The following partner images are not displaying in partner screen: 1) Big boss fitness challenge 2) National medical centre 3) Time Medico 4) Rahila research & amp
892383 | HealthSolutions Revamp | Bug |  | Closed | Immediate | Doctors list is not showing in "Book by doctors" section | Hamza Zubair | Shaji Ul Haq | 10/26/2020 8:46 | Android |  | 10/23/2020 |  |  |  | 0 | 0 | 0 | 10/23/2020 7:07 | 10/26/2020 8:46 | Hamza Zubair |  |  |  |  | No
892325 | HealthSolutions Revamp | Task |  | Resolved | Low | User image should be displayed in Doctor's "View Appointment" screen | Hamza Zubair | Shaji Ul Haq | 10/27/2020 12:40 | Android |  | 10/22/2020 |  |  |  | 0 | 0 | 0 | 10/22/2020 15:02 |  | Shaji Ul Haq |  |  |  |  | No
892324 | HealthSolutions Revamp | Task |  | New | High | Change and Forgot password APIs are remaining | Hamza Zubair | Shaji Ul Haq | 10/22/2020 15:01 | Android |  | 10/22/2020 |  |  |  | 0 | 0 | 0 | 10/22/2020 15:01 | [6 empty] | No
892320 | HealthSolutions Revamp | Feature |  | New | Normal | Add an audio and video calling featue | Hamza Zubair | Shaji Ul Haq | 10/22/2020 14:57 |  |  | 10/22/2020 |  |  |  | 0 | 0 | 0 | 10/22/2020 14:57 | [6 empty] | No
892316 | HealthSolutions Revamp | Task |  | New | High | Integrate Forgot password API | Hamza Zubair | Shaji Ul Haq | 10/22/2020 14:43 | Android |  | 10/22/2020 |  |  |  | 0 | 0 | 0 | 10/22/2020 14:43 | [6 empty] | No
892314 | HealthSolutions Revamp | Bug |  | Closed | High | The items are not adding through Product details screen in Chemist | Hamza Zubair | Shaji Ul Haq | 10/23/2020 15:13 |  |  | 10/22/2020 |  |  |  | 0 | 0 | 0 | 10/22/2020 14:31 | 10/23/2020 15:13 | Hamza Zubair |  |  |  |  | No
892313 | HealthSolutions Revamp | Bug |  | Closed | Low | Change "Image not found" to "No image available" in Product details screen in chemist | Hamza Zubair | Shaji Ul Haq | 10/23/2020 14:37 | Android |  | 10/22/2020 |  |  |  | 0 | 0 | 0 | 10/22/2020 14:30 | 10/23/2020 14:37 | Hamza Zubair |  |  |  |  | No
892311 | HealthSolutions Revamp | Task |  | New | Normal | Change the "Services" in intro screens | Hamza Zubair |  | 10/22/2020 14:22 |  |  | 10/22/2020 |  |  |  | 0 | 0 | 0 | 10/22/2020 14:22 | [6 empty] | No
892304 | HealthSolutions Revamp | Bug |  | Closed | High | Remove cart icon from "Forgot Password" screen | Hamza Zubair |  | 10/26/2020 8:30 |  |  | 10/22/2020 |  |  |  | 0 | 0 | 0 | 10/22/2020 13:37 | 10/26/2020 8:30 | Hamza Zubair |  |  |  |  | No
892303 | HealthSolutions Revamp | Bug |  | Closed | Low | Change the profile pic upload icon on sign up form | Hamza Zubair |  | 10/26/2020 8:30 |  |  | 10/22/2020 |  |  |  | 0 | 0 | 0 | 10/22/2020 13:31 | 10/26/2020 8:30 | Hamza Zubair |  |  |  |  | No
892300 | HealthSolutions Revamp | Bug |  | Closed | Low | Drawer option is not available in Diagnostics "Order by prescription" | Hamza Zubair | Shaji Ul Haq | 10/26/2020 8:36 | Android |  | 10/22/2020 |  |  |  | 0 | 0 | 0 | 10/22/2020 12:30 | 10/26/2020 8:36 | Hamza Zubair |  |  |  |  | No
892299 | HealthSolutions Revamp | Bug |  | Closed | High | My wallet screen bugs | Hamza Zubair | Shaji Ul Haq | 10/26/2020 8:13 | Android |  | 10/22/2020 |  |  |  | 0 | 0 | 0 | 10/22/2020 12:15 | 10/26/2020 8:13 | Hamza Zubair |  |  |  |  | No | 1) The top up amount field should only accept numbers. 2) On clicking enter key from phone's keypad. The user is moved to the next line. There should be no such option. 3) After entering amount and clicking on top up, a dialog box is opening. Remove this dialog box and take the user directly to the web view.
892295 | HealthSolutions Revamp | Bug |  | Closed | Low | Drawer should be displayed in "Order by prescription" | Hamza Zubair | Shaji Ul Haq | 10/27/2020 11:27 | Android |  | 10/22/2020 |  |  |  | 0 | 0 | 0 | 10/22/2020 11:09 | 10/27/2020 11:27 | Hamza Zubair |  |  |  |  | No
892293 | HealthSolutions Revamp | Bug |  | Closed | Low | Cart icon should be displayed in donate blood section | Hamza Zubair |  | 10/26/2020 8:34 |  |  | 10/22/2020 |  |  |  | 0 | 0 | 0 | 10/22/2020 11:08 | 10/26/2020 8:34 | Hamza Zubair |  |  |  |  | No
892292 | HealthSolutions Revamp | Bug |  | Closed | Low | The cart icon should also be displayed in Ambulance section | Hamza Zubair |  | 10/26/2020 8:36 |  |  | 10/22/2020 |  |  |  | 0 | 0 | 0 | 10/22/2020 11:06 | 10/26/2020 8:36 | Hamza Zubair |  |  |  |  | No
892291 | HealthSolutions Revamp | Bug |  | Closed | Low | Add a back button on the top left corner in "User profile" screen | Hamza Zubair | Shaji Ul Haq | 10/26/2020 8:37 | Android |  | 10/22/2020 |  |  |  | 0 | 0 | 0 | 10/22/2020 11:01 | 10/26/2020 8:37 | Hamza Zubair |  |  |  |  | No
892284 | HealthSolutions Revamp | Bug |  | Closed | High | App crashing on launching if the internet is off | Hamza Zubair |  | 10/22/2020 13:52 |  |  | 10/22/2020 |  |  |  | 0 | 0 | 0 | 10/22/2020 10:10 | 10/22/2020 13:52 | Hamza Zubair |  |  |  |  | No | The app should not be crashed but instead should be launched and a message should be displayed," Please check your internet connectivity"
892280 | HealthSolutions Revamp | Bug |  | Closed | Normal | Bank discount screen | Hamza Zubair | Shaji Ul Haq | 10/22/2020 14:19 | Android |  | 10/22/2020 |  |  |  | 0 | 0 | 0 | 10/22/2020 9:58 | 10/22/2020 14:19 | Hamza Zubair |  |  |  |  | No | In "Bank discount" screen in "Credit card" section, on entering the 6 digits bank code and clicking on "Check" button, the response message is hiding beneath the phone's keypad. Hide the keyboard on clicking on "Check" button so that the message could be seen by the user. And on again clicking on the digits section, the keypad should be opened
892277 | HealthSolutions Revamp | Feature |  | New | Normal | Add a Covid PCR section | Hamza Zubair | Shaji Ul Haq | 10/22/2020 9:46 | Android |  | 10/22/2020 |  |  |  | 0 | 0 | 0 | 10/22/2020 9:46 | [6 empty] | No
892275 | HealthSolutions Revamp | Bug |  | Resolved | High | An un expected error is coming on going to "Report" segment in "Diagnostics" section | Hamza Zubair | Shaji Ul Haq | 10/29/2020 7:47 | Android |  | 10/22/2020 |  |  |  | 0 | 0 | 0 | 10/22/2020 9:34 |  | Shaji Ul Haq |  |  |  |  | No
892273 | HealthSolutions Revamp | Bug |  | Closed | Urgent | Remove cart icon from the payment screen | Hamza Zubair | Shaji Ul Haq | 10/22/2020 14:34 | Android |  | 10/22/2020 |  |  |  | 0 | 0 | 0 | 10/22/2020 9:29 | 10/22/2020 14:34 | Hamza Zubair |  |  |  |  | No
892271 | HealthSolutions Revamp | Task |  | New | High | Notifications work is not done yet | Hamza Zubair | Shaji Ul Haq | 10/22/2020 9:20 | Android |  | 10/22/2020 |  |  |  | 0 | 0 | 0 | 10/22/2020 9:20 | [6 empty] | No
892268 | HealthSolutions Revamp | Task |  | Closed | Normal | The cart icon should also be displayed in G-segment | Hamza Zubair |  | 10/23/2020 7:39 |  |  | 10/22/2020 |  |  |  | 0 | 0 | 0 | 10/22/2020 9:16 | 10/23/2020 7:39 | Hamza Zubair |  |  |  |  | No
892266 | HealthSolutions Revamp | Bug |  | Closed | High | Getting un expected error in "Add address" screen | Hamza Zubair | Shaji Ul Haq | 10/22/2020 11:15 |  |  | 10/22/2020 |  |  |  | 0 | 0 | 0 | 10/22/2020 9:07 | 10/22/2020 11:15 | Hamza Zubair |  |  |  |  | No
892257 | HealthSolutions Revamp | Bug |  | Closed | Low | The user profile pic should be opened on clicking on the image in User's profile | Hamza Zubair | Shaji Ul Haq | 10/22/2020 11:27 | Android |  | 10/22/2020 |  |  |  | 0 | 0 | 0 | 10/22/2020 7:56 | 10/22/2020 11:27 | Hamza Zubair |  |  |  |  | No
892256 | HealthSolutions Revamp | Task |  | Closed | Low | Change the theme of the Doctor Advice section to red and white | Hamza Zubair | Shaji Ul Haq | 10/22/2020 14:35 | Android |  | 10/22/2020 |  |  |  | 0 | 0 | 0 | 10/22/2020 7:42 | 10/22/2020 14:35 | Hamza Zubair |  |  |  |  | No | On clicking on any video, that video should be highlighted in red (Theme color) with white text
892255 | HealthSolutions Revamp | Bug |  | Closed | Normal | Drawer option is not available in Doctor Advice screen | Hamza Zubair | Shaji Ul Haq | 10/22/2020 14:37 | Android |  | 10/22/2020 |  |  |  | 0 | 0 | 0 | 10/22/2020 7:39 | 10/22/2020 14:37 | Hamza Zubair |  |  |  |  | No
892252 | HealthSolutions Revamp | Task |  | New | High | SMS to users on signing up and placing order | Hamza Zubair |  | 10/22/2020 7:29 |  |  | 10/22/2020 |  |  |  | 0 | 0 | 0 | 10/22/2020 7:29 | [6 empty] | No
892250 | HealthSolutions Revamp | Bug |  | Closed | Normal | On clicking on "Cancel" option from "Choose your profile pic" window on sign up screen, if the image is already uploaded than it should be removed. | Hamza Zubair |  | 10/22/2020 7:27 |  |  | 10/22/2020 |  |  |  | 0 | 0 | 0 | 10/22/2020 7:26 | 10/22/2020 7:27 | Hamza Zubair |  |  |  |  | No
892245 | HealthSolutions Revamp | Bug |  | Closed | High | Phone number field is accepting string data | Hamza Zubair |  | 10/22/2020 14:27 |  |  | 10/22/2020 |  |  |  | 0 | 0 | 0 | 10/22/2020 7:01 | 10/22/2020 14:27 | Hamza Zubair |  |  |  |  | No | In "Contact Us" form, the phone number field should only accept numeric data
892185 | HealthSolutions Revamp | Bug |  | Closed | Normal | Change the "Request a call" message on submitting the call request | Hamza Zubair | Shaji Ul Haq | 10/22/2020 7:28 |  |  | 10/21/2020 |  |  |  | 0 | 0 | 0 | 10/21/2020 14:59 | 10/22/2020 7:28 | Hamza Zubair |  |  |  |  | No | Change the request received message to, "Request submitted successfully! We will contact you soon. Thanks!"
892182 | HealthSolutions Revamp | Bug |  | Closed | High | On the login screen, the phone icon should be on the top right corner. | Hamza Zubair | Shaji Ul Haq | 10/22/2020 6:56 | Android |  | 10/21/2020 |  |  |  | 0 | 0 | 0 | 10/21/2020 14:56 | 10/22/2020 6:56 | Hamza Zubair |  |  |  |  | No
892169 | HealthSolutions Revamp | Task |  | Closed | Low | Profile picture on sign up and in user's profile should be elevated | Hamza Zubair | Shaji Ul Haq | 10/22/2020 14:48 | Android |  | 10/21/2020 |  |  |  | 0 | 0 | 0 | 10/21/2020 13:52 | 10/22/2020 14:48 | Hamza Zubair |  |  |  |  | No
892152 | HealthSolutions Revamp | Task |  | New | Normal | Max no of notifications | Hamza Zubair | Shaji Ul Haq | 10/21/2020 12:48 | Android |  | 10/21/2020 |  |  |  | 0 | 0 | 0 | 10/21/2020 12:48 | [6 empty] | No | Only latest 20 notifications should be displayed in "Notifications" section.
892151 | HealthSolutions Revamp | Bug |  | Closed | Low | Remove the black borders from each partner window in "Partner List" and make each partner logo elevated | Hamza Zubair | Shaji Ul Haq | 10/22/2020 7:16 | Android |  | 10/21/2020 |  |  |  | 0 | 0 | 0 | 10/21/2020 12:29 | 10/22/2020 7:16 | Hamza Zubair |  |  |  |  | No
892092 | HealthSolutions Revamp | Bug |  | Closed | High | There should be an option to capture profile image on sign up using front and back camera of the phone | Hamza Zubair | Shaji Ul Haq | 10/22/2020 14:51 | Android |  | 10/21/2020 |  |  |  | 0 | 0 | 0 | 10/21/2020 7:59 | 10/22/2020 14:51 | Hamza Zubair |  |  |  |  | No
892091 | HealthSolutions Revamp | Bug |  | Closed | High | Uploaded profile picture is not showing in user's profile | Hamza Zubair | Shaji Ul Haq | 10/22/2020 11:28 | Android |  | 10/21/2020 |  |  |  | 0 | 0 | 0 | 10/21/2020 7:48 | 10/22/2020 11:28 | Hamza Zubair |  |  |  |  | No
892090 | HealthSolutions Revamp | Bug |  | Closed | High | Last name is not showing in Name field in user's profile | Hamza Zubair | Shaji Ul Haq | 10/21/2020 14:34 | Android |  | 10/21/2020 |  |  |  | 0 | 0 | 0 | 10/21/2020 7:45 | 10/21/2020 14:34 | Hamza Zubair |  |  |  |  | No
892012 | HealthSolutions Revamp | Bug |  | New | High | Cart no not updating on removing the cart items from G-segment. | Hamza Zubair | Shaji Ul Haq | 10/20/2020 15:06 | Android |  | 10/20/2020 |  |  |  | 0 | 0 | 0 | 10/20/2020 15:06 | [6 empty] | No
892011 | HealthSolutions Revamp | Bug |  | Closed | High | Default address added by the user is not displaying as Current address at the time of placing order in "Checkout" screen | Hamza Zubair | Shaji Ul Haq | 10/26/2020 8:36 | Android |  | 10/20/2020 |  |  |  | 0 | 0 | 0 | 10/20/2020 14:56 | 10/26/2020 8:36 | Hamza Zubair |  |  |  |  | No
892009 | HealthSolutions Revamp | Bug |  | Closed | High | Old product detail screen is showing in chemist section on clicking on the product window on area other than buttons and image. | Hamza Zubair | Shaji Ul Haq | 10/22/2020 14:33 | Android |  | 10/20/2020 |  |  |  | 0 | 0 | 0 | 10/20/2020 14:50 | 10/22/2020 14:33 | Hamza Zubair |  |  |  |  | No
891875 | HealthSolutions Revamp | Task |  | Closed | Normal | Doctor image shape in "Book Appointment", & "Doctor list" screen. | Hamza Zubair | Shaji Ul Haq | 10/20/2020 14:37 | Android |  | 10/19/2020 |  |  |  | 0 | 0 | 0 | 10/19/2020 11:08 | 10/20/2020 14:37 | Hamza Zubair |  |  |  |  | No | Change the shape of the doctor's image in a way that the edges should be a little circular and the image should be elevated.
891872 | HealthSolutions Revamp | Bug |  | Closed | Low | The "View more" and "View less" icon available in the left side of these buttons is not visible in "Equipment details" screen | Hamza Zubair | Shaji Ul Haq | 10/23/2020 13:47 | Android |  | 10/19/2020 |  |  |  | 0 | 0 | 0 | 10/19/2020 11:01 | 10/23/2020 13:47 | Hamza Zubair |  |  |  |  | No
891867 | HealthSolutions Revamp | Bug |  | Closed | Normal | Add a loader in "Speciality" screen after clicking on any speciality to search to let the user know that the doctor list is being searched according to the selected speciality | Hamza Zubair | Shaji Ul Haq | 10/20/2020 14:42 | Android |  | 10/19/2020 |  |  |  | 0 | 0 | 0 | 10/19/2020 10:49 | 10/20/2020 14:42 | Hamza Zubair |  |  |  |  | No
891864 | HealthSolutions Revamp | Bug |  | Closed | High | Remove "Out of stock" text in equipment details screen. The equipment product is adding in cart but displaying as "Out of stock" | Hamza Zubair | Shaji Ul Haq | 10/22/2020 14:51 | Android |  | 10/19/2020 |  |  |  | 0 | 0 | 0 | 10/19/2020 10:32 | 10/22/2020 14:51 | Hamza Zubair |  |  |  |  | No
891863 | HealthSolutions Revamp | Bug |  | New | High | Cart items no count not updating | Hamza Zubair | Shaji Ul Haq | 10/19/2020 10:27 |  |  | 10/19/2020 |  |  |  | 0 | 0 | 0 | 10/19/2020 10:27 | [6 empty] | No | 1) Add equipment product from "Equipment details" screen 2) Go to cart 3) Empty cart 4) Move back to Equipment details screen Actual Result: The no count on the cart icon is not updating. Expected Result: The no count on the cart icon should be updated.
891862 | HealthSolutions Revamp | Bug |  | Closed | High | "Go to cart" option not displaying when adding equipment product from the equipment details screen | Hamza Zubair | Shaji Ul Haq | 10/20/2020 14:45 | Android |  | 10/19/2020 |  |  |  | 0 | 0 | 0 | 10/19/2020 10:03 | 10/20/2020 14:45 | Hamza Zubair |  |  |  |  | No
891858 | HealthSolutions Revamp | Bug |  | Closed | Low | Wrong position of the cart item no counter | Hamza Zubair | Shaji Ul Haq | 10/20/2020 14:45 | Android |  | 10/19/2020 |  |  |  | 0 | 0 | 0 | 10/19/2020 10:00 | 10/20/2020 14:45 | Hamza Zubair |  |  |  |  | No | Adjust the cart item no counter above the cart icon at the top right corner of the cart icon. Currently it is positioned at the middle of the cart icon.
891857 | HealthSolutions Revamp | Task |  | Closed | High | Add the attached "No image available" pic in equipment section in which there is no product image. | Hamza Zubair | Shaji Ul Haq | 10/23/2020 7:39 | Android |  | 10/19/2020 |  |  |  | 0 | 0 | 0 | 10/19/2020 9:57 | 10/23/2020 7:39 | Hamza Zubair |  | No image available.png |  |  | No
891855 | HealthSolutions Revamp | Bug |  | Closed | High | The drawer option is not available in "Equipment to buy" screen | Hamza Zubair | Shaji Ul Haq | 10/20/2020 14:53 | Android |  | 10/19/2020 |  |  |  | 0 | 0 | 0 | 10/19/2020 9:53 | 10/20/2020 14:53 | Hamza Zubair |  |  |  |  | No
891854 | HealthSolutions Revamp | Bug |  | Closed | High | Add a "No image available" picture in each segment, if the product image isn't available | Hamza Zubair | Shaji Ul Haq | 10/22/2020 14:28 | Android |  | 10/19/2020 |  |  |  | 0 | 0 | 0 | 10/19/2020 9:48 | 10/22/2020 14:28 | Hamza Zubair |  |  |  |  | No
891853 | HealthSolutions Revamp | Bug |  | New | High | The products in each section are taking too much time to upload. | Hamza Zubair | Shaji Ul Haq | 10/19/2020 9:47 | Android |  | 10/19/2020 |  |  |  | 0 | 0 | 0 | 10/19/2020 9:47 | [6 empty] | No | Add pagination so that the products can be loaded faster.
891852 | HealthSolutions Revamp | Bug |  | Closed | Normal | The ratio of the uploaded prescription images in patient details screen in "Previous reports/ Medican" section should be 1:1. Currently it's showing in a rectangular view | Hamza Zubair | Shaji Ul Haq | 10/20/2020 14:54 | Android |  | 10/19/2020 |  |  |  | 0 | 0 | 0 | 10/19/2020 9:35 | 10/20/2020 14:54 | Hamza Zubair |  |  |  |  | No | Also change "Medican" to "Medicine" in text "Previous reports/medican".
891851 | HealthSolutions Revamp | Feature |  | New | Normal | The selected date from the calender in "Book Appointment" screen should be highlighted in G-segment | Hamza Zubair | Shaji Ul Haq | 10/19/2020 9:29 | Android |  | 10/19/2020 |  |  |  | 0 | 0 | 0 | 10/19/2020 9:29 | [6 empty] | No
891850 | HealthSolutions Revamp | Feature |  | Closed | Normal | Add "Easy Paisa" & "Jazz Cash" in payment methods | Hamza Zubair | Shaji Ul Haq | 10/22/2020 14:34 | Android |  | 10/19/2020 |  |  |  | 0 | 0 | 0 | 10/19/2020 9:26 | 10/22/2020 14:34 | Hamza Zubair |  |  |  |  | No
891849 | HealthSolutions Revamp | Task |  | Closed | Normal | Remove Urdu text from G-segment | Hamza Zubair | Shaji Ul Haq | 10/20/2020 15:22 | Android |  | 10/19/2020 |  |  |  | 0 | 0 | 0 | 10/19/2020 9:25 | 10/20/2020 15:22 | Hamza Zubair |  |  |  |  | No
891614 | HealthSolutions Revamp | Task |  | Closed | Urgent | Customer appointment details API for doctor login | Hamza Zubair | Shaji Ul Haq | 10/21/2020 15:01 | Android |  | 10/19/2020 |  |  |  | 0 | 0 | 0 | 10/19/2020 8:32 | 10/21/2020 15:01 | Hamza Zubair |  |  |  |  | No
891613 | HealthSolutions Revamp | Feature |  | Closed | High | Add login as doctor module | Hamza Zubair | Shaji Ul Haq | 10/21/2020 10:35 | Android |  | 10/19/2020 |  |  |  | 0 | 0 | 0 | 10/19/2020 8:30 | 10/21/2020 10:35 | Shaji Ul Haq |  |  |  |  | No | Add "View appointments" screen if the user login as a doctor and opens "G-segment". All the approved appointments by the admin should be displayed on this screen with an audio and video calling option.
891587 | HealthSolutions Revamp | Bug |  | Resolved | High | Home screen icon rotation effect on clicking not working in some phones | Hamza Zubair | Shaji Ul Haq | 10/27/2020 14:00 | Android |  | 10/19/2020 |  |  |  | 0 | 0 | 0 | 10/19/2020 7:52 |  | Shaji Ul Haq |  |  |  |  | No
891583 | HealthSolutions Revamp | Task |  | New | Immediate | Remove OTP from sign up | Hamza Zubair | Syed Rafay | 10/19/2020 7:21 | iOS |  | 10/19/2020 |  |  |  | 0 | 0 | 0 | 10/19/2020 7:21 | [6 empty] | No
891452 | HealthSolutions Revamp | Bug |  | Closed | Urgent | Rs. 50 per kg are not adding in delivery charges on increasing product quanitity | Hamza Zubair | Shaji Ul Haq | 10/16/2020 13:18 | API |  | 10/16/2020 |  |  |  | 0 | 0 | 0 | 10/16/2020 12:28 | 10/16/2020 13:18 | Hamza Zubair |  |  |  |  | No
891433 | HealthSolutions Revamp | Feature |  | Closed | High | Add a search by doctor name option in "Book by doctor" section | Hamza Zubair | Shaji Ul Haq | 10/19/2020 9:35 | Android |  | 10/16/2020 |  |  |  | 0 | 0 | 0 | 10/16/2020 10:10 | 10/19/2020 9:35 | Hamza Zubair |  |  |  |  | No | The user should be able to search a doctor by name
891432 | HealthSolutions Revamp | Task |  | Closed | High | Online doctor | Hamza Zubair | Shaji Ul Haq | 10/22/2020 14:21 | Android |  | 10/16/2020 |  |  |  | 0 | 0 | 0 | 10/16/2020 10:09 | 10/22/2020 14:21 | Hamza Zubair |  |  |  |  | No | 1) The picture of the doctor in "Online doctor" section should be same as in "Doctor list". Currently both images are different. 2) The user should be able to book any doctor from the "Online doctors" list. 3) Add a small green circle on each online doctor in "Online Doctors" list.
891428 | HealthSolutions Revamp | Bug |  | Closed | Normal | Address not needed when submitting "Request a call" request when the user is logged in | Hamza Zubair | Shaji Ul Haq | 10/22/2020 14:34 |  |  | 10/16/2020 |  |  |  | 0 | 0 | 0 | 10/16/2020 9:29 | 10/22/2020 14:34 | Hamza Zubair |  |  |  |  | No | When the user is logged in and on submitting "Request a call" request and the address is not added than on filling the form and submitting the request, the user is moved to the address screen but it should not and the request should be submitted directly i.e there is no need to take address from the user.
891424 | HealthSolutions Revamp | Bug |  | Closed | High | An unexpected error is coming on going to "Request a call" screen, if the user is not logged in | Hamza Zubair | Shaji Ul Haq | 10/21/2020 15:01 | Android |  | 10/16/2020 |  |  |  | 0 | 0 | 0 | 10/16/2020 9:13 | 10/21/2020 15:01 | Hamza Zubair |  |  |  |  | No
891422 | HealthSolutions Revamp | Bug |  | Closed | High | Current address not removing on deleting already added addresses on checkout screen. | Hamza Zubair |  | 10/26/2020 8:31 |  |  | 10/16/2020 |  |  |  | 0 | 0 | 0 | 10/16/2020 9:08 | 10/26/2020 8:31 | Hamza Zubair |  |  |  |  | No
891420 | HealthSolutions Revamp | Bug |  | Closed | High | Popularity box is not properly visible in G-segment sort screen | Hamza Zubair | Shaji Ul Haq | 10/21/2020 15:05 | [6 empty] | 0 | 0 | 0 | 10/16/2020 8:55 | 10/21/2020 15:05 | Hamza Zubair |  |  |  |  | No
891311 | HealthSolutions Revamp | Bug |  | Closed | Normal | Remove the text, "And more joining soon" from partners section | Hamza Zubair | Shaji Ul Haq | 10/20/2020 15:04 |  |  | 10/15/2020 |  |  |  | 0 | 0 | 0 | 10/15/2020 14:12 | 10/20/2020 15:04 | Hamza Zubair |  |  |  |  | No
891286 | HealthSolutions Revamp | Feature |  | Closed | High | Add "Country" field in user's profile | Hamza Zubair | Shaji Ul Haq | 10/22/2020 11:12 | Android |  | 10/15/2020 |  |  |  | 0 | 0 | 0 | 10/15/2020 8:47 | 10/22/2020 11:12 | Hamza Zubair |  |  |  |  | No
891284 | HealthSolutions Revamp | Feature |  | Closed | High | Add "Address" field in Sign up form | Hamza Zubair | Shaji Ul Haq | 10/20/2020 15:18 | Android |  | 10/15/2020 |  |  |  | 0 | 0 | 0 | 10/15/2020 7:47 | 10/20/2020 15:18 | Shaji Ul Haq |  |  |  |  | No | Add a "Address" field on sign up form. On clicking on this field, the map will be opened and the user will select the location through google maps. This address will be saved as the user's default address and at the time of placing order, this address will be displayed as current address.
891230 | HealthSolutions Revamp | Bug |  | Closed | Normal | Delivery charges not updating on removing the products from cart | Hamza Zubair | Shaji Ul Haq | 10/19/2020 12:19 | Android |  | 10/14/2020 |  |  |  | 0 | 0 | 0 | 10/14/2020 15:14 | 10/19/2020 12:19 | Hamza Zubair |  |  |  |  | No | Add some product from "Blood" section in cart and than from "Chemist". Remove the blood products from the cart and leave the chemist products. Now the delivery charges should be updated but it's still showing Rs. 550 but the blood products have been removed so it should display Rs. 200
891229 | HealthSolutions Revamp | Task |  | Closed | High | Add product details screen in "Chemist" section | Hamza Zubair | Shaji Ul Haq | 10/15/2020 13:26 | Android |  | 10/14/2020 |  |  |  | 0 | 0 | 0 | 10/14/2020 15:09 | 10/15/2020 13:26 | Hamza Zubair |  |  |  |  | No
891228 | HealthSolutions Revamp | Feature |  | Closed | Urgent | Remove karachi restriction from map and change it to all over Pakistan | Hamza Zubair | Shaji Ul Haq | 10/20/2020 15:12 | Android |  | 10/14/2020 |  |  |  | 0 | 0 | 0 | 10/14/2020 14:54 | 10/20/2020 15:12 | Hamza Zubair |  |  |  |  | No
891227 | HealthSolutions Revamp | Bug |  | Resolved | Normal | Internet stopped working in "Blood Request" section | Hamza Zubair | Shaji Ul Haq | 10/28/2020 10:19 |  |  | 10/14/2020 |  |  |  | 0 | 0 | 0 | 10/14/2020 14:50 |  | Shaji Ul Haq |  |  |  |  | No | In "Blood Request" section, if the internet connection is lost or stops working, than the blood products are not displaying. In this case a message should be displayed as, "Please check your internet connectivity" to let the user know that the internet connection is lost. NOTE: This message should be displayed in all the segments in this case when internet connection is lost.
891189 | HealthSolutions Revamp | Feature |  | Rejected | High | Online doctors | Hamza Zubair | Shaji Ul Haq | 10/15/2020 9:57 | Android |  | 10/14/2020 |  |  |  | 0 | 0 | 0 | 10/14/2020 7:48 | 10/15/2020 9:57 | Shaji Ul Haq |  |  |  |  | No | 1) The online doctors should be displayed separately on the customer's side 2) If the customer selects online doctor than all the doctors that are online should be displayed and the user should be able to book that doctor instantly. 3) On booking an online doctor, the user will not need to select any time slot. 4) After selecting any from the online doctors list, the user will be moved directly to the payment method screen from which he'll select the payment method and after completing the payment procedure, will be connected to the online doctor by in app calling feature of the app instantly.
891188 | HealthSolutions Revamp | Bug |  | Rejected | Normal | Remove filter by distance option from filters screen in G-segment | Hamza Zubair | Shaji Ul Haq | 10/15/2020 11:38 | Android |  | 10/14/2020 |  |  |  | 0 | 0 | 0 | 10/14/2020 7:38 | 10/15/2020 11:38 | Shaji Ul Haq |  |  |  |  | No
891186 | HealthSolutions Revamp | Feature |  | Closed | High | Doctor's consultation fee | Hamza Zubair | Shaji Ul Haq | 10/14/2020 14:08 | Android |  | 10/14/2020 |  |  |  | 0 | 0 | 0 | 10/14/2020 7:35 | 10/14/2020 14:08 | Hamza Zubair |  |  |  |  | No | The doctor's consultation fee should also be displayed on the home screen in each doctor's window.
891185 | HealthSolutions Revamp | Feature |  | Closed | High | User should only be able to book a doctor appointment with in 4 months including current month | Hamza Zubair | Shaji Ul Haq | 10/14/2020 14:09 | Android |  | 10/14/2020 |  |  |  | 0 | 0 | 0 | 10/14/2020 7:33 | 10/14/2020 14:09 | Hamza Zubair |  |  |  |  | No
891184 | HealthSolutions Revamp | Feature |  | New | High | Past time slots should not be displayed in G-segment | Hamza Zubair | Shaji Ul Haq | 10/14/2020 7:32 |  |  | 10/14/2020 |  |  |  | 0 | 0 | 0 | 10/14/2020 7:32 | [6 empty] | No
891183 | HealthSolutions Revamp | Feature |  | Closed | High | The past dates in the calender should be disabled in G-segment | Hamza Zubair | Shaji Ul Haq | 10/15/2020 13:58 | Android |  | 10/14/2020 |  |  |  | 0 | 0 | 0 | 10/14/2020 7:31 | 10/15/2020 13:58 | Hamza Zubair |  |  |  |  | No
891182 | HealthSolutions Revamp | Feature |  | In Progress | High | Doctor's time slot selection screen should be switched with the patient details screen in G-segment | Hamza Zubair | Shaji Ul Haq | 10/14/2020 9:05 | Android |  | 10/14/2020 |  |  |  | 0 | 0 | 0 | 10/14/2020 7:29 |  | Shaji Ul Haq |  |  |  |  | No
891181 | HealthSolutions Revamp | Bug |  | Closed | Normal | Change "Department" to "Speciality" in G-segment | Hamza Zubair | Shaji Ul Haq | 10/14/2020 14:10 | Android |  | 10/14/2020 |  |  |  | 0 | 0 | 0 | 10/14/2020 7:26 | 10/14/2020 14:10 | Hamza Zubair |  |  |  |  | No
891133 | HealthSolutions Revamp | Bug |  | Rejected | Low | Equipment list view | Hamza Zubair | Shaji Ul Haq | 10/15/2020 9:55 | Android |  | 10/13/2020 |  |  |  | 0 | 0 | 0 | 10/13/2020 12:59 | 10/15/2020 9:55 | Shaji Ul Haq |  |  |  |  | No | Change the view of the equipment list in "Equipment to buy" section and make it same as Chemist.
891132 | HealthSolutions Revamp | Bug |  | Closed | Normal | Empty cart | Hamza Zubair | Shaji Ul Haq | 10/22/2020 11:28 | Android |  | 10/13/2020 |  |  |  | 0 | 0 | 0 | 10/13/2020 12:56 | 10/22/2020 11:28 | Hamza Zubair |  |  |  |  | No | When there is no item in the cart than on clicking on the cart icon the cart screen should not be opened and a message should be displayed as, "Please add items first"
891131 | HealthSolutions Revamp | Bug |  | Closed | Normal | Cart icon in equipment details screen | Hamza Zubair | Shaji Ul Haq | 10/15/2020 13:53 | Android | [5 empty] | 0 | 0 | 0 | 10/13/2020 12:44 | 10/15/2020 13:53 | Hamza Zubair |  |  |  |  | No | Change the cart icon available on the equipment details screen to new one.
891121 | HealthSolutions Revamp | Bug |  | Closed | High | App crashing on opening the map second time | Hamza Zubair | Shaji Ul Haq | 10/15/2020 14:21 | Android |  | 10/13/2020 |  |  |  | 0 | 0 | 0 | 10/13/2020 11:16 | 10/15/2020 14:21 | Hamza Zubair |  |  |  |  | No | Open the map from any segment, go back and than again click on the "Location" field, the app will be crashed.
891120 | HealthSolutions Revamp | Task |  | Closed | Low | Remove "History" option for now from drawer | Hamza Zubair | Shaji Ul Haq | 10/14/2020 14:25 | Android |  | 10/13/2020 |  |  |  | 0 | 0 | 0 | 10/13/2020 11:08 | 10/14/2020 14:25 | Hamza Zubair |  |  |  |  | No
891118 | HealthSolutions Revamp | Bug |  | Closed | Normal | Icon alignment is out in "Home care" and "Fitness" home screens | Hamza Zubair | Shaji Ul Haq | 10/15/2020 14:22 | Android |  | 10/13/2020 |  |  |  | 0 | 0 | 0 | 10/13/2020 11:05 | 10/15/2020 14:22 | Hamza Zubair |  |  |  |  | No
891116 | HealthSolutions Revamp | Bug |  | Closed | Immediate | Unable to submit diagnostic request via "Order by search" | Hamza Zubair |  | 10/15/2020 14:23 | Android |  | 10/13/2020 |  |  |  | 0 | 0 | 0 | 10/13/2020 11:01 | 10/15/2020 14:23 | Hamza Zubair |  |  |  |  | No | The order by search screen should be scrollable as "Submit" button is not visible and clickable.
891115 | HealthSolutions Revamp | Bug |  | Closed | Urgent | App crashing on clicking "Write your order" option in Home care section | Hamza Zubair | Shaji Ul Haq | 10/15/2020 14:26 | Android |  | 10/13/2020 |  |  |  | 0 | 0 | 0 | 10/13/2020 10:56 | 10/15/2020 14:26 | Hamza Zubair |  |  |  |  | No
891114 | HealthSolutions Revamp | Bug |  | Closed | High | Add "Rs" before amount every where where amount is mentioned | Hamza Zubair | Shaji Ul Haq | 10/20/2020 15:23 | Android |  | 10/13/2020 |  |  |  | 0 | 0 | 0 | 10/13/2020 10:55 | 10/20/2020 15:23 | Hamza Zubair |  |  |  |  | No
891110 | HealthSolutions Revamp | Bug |  | Closed | High | App crashing on opening and tapping on the map twice fastly | Hamza Zubair | Shaji Ul Haq | 10/15/2020 14:39 | Android |  | 10/13/2020 |  |  |  | 0 | 0 | 0 | 10/13/2020 10:18 | 10/15/2020 14:39 | Hamza Zubair |  |  |  |  | No
891109 | HealthSolutions Revamp | Bug |  | Closed | Urgent | Map not redirecting the user to his current location automatically | Hamza Zubair | Shaji Ul Haq | 10/21/2020 14:55 | Android |  | 10/13/2020 |  |  |  | 0 | 0 | 0 | 10/13/2020 10:10 | 10/21/2020 14:55 | Hamza Zubair |  |  |  |  | No | On opening the map from any of the segments, the map is not automatically redirecting the user to his current location.
891107 | HealthSolutions Revamp | Task |  | Closed | Normal | Wrong screen color in "Add Address" location screen. | Hamza Zubair | Shaji Ul Haq | 10/15/2020 14:40 | Android |  | 10/13/2020 |  |  |  | 0 | 0 | 0 | 10/13/2020 10:02 | 10/15/2020 14:40 | Hamza Zubair |  |  |  |  | No | In "Add address" screen, on clicking on "My location" field, the map screen is opening but in green color. Change it to red
891106 | HealthSolutions Revamp | Feature |  | Rejected | Normal | User profile details should be editable | Hamza Zubair | Shaji Ul Haq | 10/14/2020 9:34 | Android |  | 10/13/2020 |  |  |  | 0 | 0 | 0 | 10/13/2020 9:58 | 10/14/2020 9:34 | Shaji Ul Haq |  |  |  |  | No | The user should be able to edit his profile details on the profile screen.
891105 | HealthSolutions Revamp | Feature |  | Closed | Normal | Image uploading option in user's profile | Hamza Zubair | Shaji Ul Haq | 10/21/2020 15:02 | Android |  | 10/13/2020 |  |  |  | 0 | 0 | 0 | 10/13/2020 9:56 | 10/21/2020 15:02 | Hamza Zubair |  |  |  |  | No | Add an option to upload image in user's profile.
891103 | HealthSolutions Revamp | Feature |  | Closed | Normal | Change "Call" button to "Cart" available on the top right corner of the home screen | Hamza Zubair | Shaji Ul Haq | 10/20/2020 15:04 | Android |  | 10/13/2020 |  |  |  | 0 | 0 | 0 | 10/13/2020 9:48 | 10/20/2020 15:04 | Hamza Zubair |  |  |  |  | No
891101 | HealthSolutions Revamp | Bug |  | Closed | Urgent | Insert phone number validation on sign up i.e same number can't be used twice for registeration | Hamza Zubair | Hamza Zubair | 10/21/2020 8:50 | API |  | 10/13/2020 |  |  |  | 0 | 0 | 0 | 10/13/2020 9:34 | 10/21/2020 8:50 | Shaji Ul Haq |  |  |  |  | No
891100 | HealthSolutions Revamp | Task |  | Closed | High | Change the country selection drop down on sign up so that the user can search the country by entering name | Hamza Zubair | Shaji Ul Haq | 10/22/2020 14:37 | Android |  | 10/13/2020 |  |  |  | 0 | 0 | 0 | 10/13/2020 9:31 | 10/22/2020 14:37 | Hamza Zubair |  |  |  |  | No
891098 | HealthSolutions Revamp | Bug |  | Closed | High | Write your order and contact us screens should be scrollable | Hamza Zubair | Shaji Ul Haq | 10/15/2020 14:41 | Android |  | 10/13/2020 |  |  |  | 0 | 0 | 0 | 10/13/2020 9:22 | 10/15/2020 14:41 | Hamza Zubair |  |  |  |  | No
891096 | HealthSolutions Revamp | Feature |  | New | Normal | Add "Frequent tests" section in Diagnostics, displaying the list of most common tests. | Hamza Zubair | Shaji Ul Haq | 10/13/2020 8:08 | Android |  | 10/13/2020 |  |  |  | 0 | 0 | 0 | 10/13/2020 8:08 | [6 empty] | No
891095 | HealthSolutions Revamp | Bug |  | Closed | Low | Add a "?" after "Quick question" in contact us screen | Hamza Zubair | Shaji Ul Haq | 10/14/2020 14:12 |  |  | 10/13/2020 |  |  |  | 0 | 0 | 0 | 10/13/2020 8:06 | 10/14/2020 14:12 | Hamza Zubair |  |  |  |  | No
891094 | HealthSolutions Revamp | Bug |  | Closed | High | Change "Contact Us" screen style same as the home screen of the other segments i.e square boxes with icon | Hamza Zubair |  | 10/15/2020 14:42 |  |  | 10/13/2020 |  |  |  | 0 | 0 | 0 | 10/13/2020 8:03 | 10/15/2020 14:42 | Hamza Zubair |  |  |  |  | No
891092 | HealthSolutions Revamp | Bug |  | Closed | Urgent | Contact us screen is opening instead of Write your order screen in "Home care & Nursing" section | Hamza Zubair |  | 10/14/2020 14:12 |  |  | 10/13/2020 |  |  |  | 0 | 0 | 0 | 10/13/2020 8:01 | 10/14/2020 14:12 | Hamza Zubair |  |  |  |  | No
891091 | HealthSolutions Revamp | Feature |  | Resolved | High | Add an "Imaging" segment in "Diagnostics" segment | Hamza Zubair | Shaji Ul Haq | 10/28/2020 10:20 |  |  | 10/13/2020 |  |  |  | 0 | 0 | 0 | 10/13/2020 7:54 |  | Shaji Ul Haq |  |  |  |  | No | On clicking on imaging option, a screen will be opened having two options 1) X-ray 2) Ultra-sound The flow should be same as e-commerce for this section. These products will be added to cart.
891033 | HealthSolutions Revamp | Feature |  | Closed | Normal | Add "View cart" button in product list screen in "Equipment" and | Hamza Zubair |  | 10/15/2020 11:52 | [6 empty] | 0 | 0 | 0 | 10/12/2020 12:01 | 10/15/2020 11:52 | Shaji Ul Haq |  |  |  |  | No
888681 | HealthSolutions Revamp | Bug |  | Closed | High | Added product are not displaying on cart icon | Shahzaib Idrees | Shaji Ul Haq | 10/22/2020 13:51 | Android |  | 9/24/2020 |  |  |  | 0 | 0 | 0 | 9/24/2020 8:40 | 10/22/2020 13:51 | Hamza Zubair |  |  |  |  | No | In "Equipment" section go on "Equipment to buy" and click Add to cart button, order are move in cart icon but cart icon are not displaying number of products.
888541 | HealthSolutions Revamp | Bug |  | Closed | High | Description field is mandatory but there is no " * " symbol on this field in G-segment | Hamza Zubair | Shaji Ul Haq | 10/15/2020 14:45 | Android |  | 9/23/2020 |  |  |  | 0 | 0 | 0 | 9/23/2020 11:32 | 10/15/2020 14:45 | Hamza Zubair |  |  |  |  | No | On booking any doctor, in the customer details screen, the "Description" field is mandatory but there is no " * " symbol on this field. Add " * " symbol on this field as it's mandatory and user can't move to the next page with out filling it.
888534 | HealthSolutions Revamp | Bug |  | Closed | Immediate | App crashing on selecting order by prescription in Chemist section | Hamza Zubair |  | 10/15/2020 14:45 | Android |  | 9/23/2020 |  |  |  | 0 | 0 | 0 | 9/23/2020 11:06 | 10/15/2020 14:45 | Hamza Zubair |  |  |  |  | No
888533 | HealthSolutions Revamp | Bug |  | Closed | High | No cart screen in "Request Blood" | Hamza Zubair | Shaji Ul Haq | 10/20/2020 15:21 | Android |  | 9/23/2020 |  |  |  | 0 | 0 | 0 | 9/23/2020 11:04 | 10/20/2020 15:21 | Hamza Zubair |  |  |  |  | No | In "Request Blood" section, after selecting the blood product, the user is directly moved to check out instead of cart screen.
888531 | HealthSolutions Revamp | Task |  | Closed | High | Cart validation | Shahzaib Idrees | Shaji Ul Haq | 10/15/2020 14:45 | Android |  | 9/23/2020 |  |  |  | 0 | 0 | 0 | 9/23/2020 10:48 | 10/15/2020 14:45 | Hamza Zubair |  |  |  |  | No | In "Chemist" section go on "Shop online" section, no validation define in cart button.
888530 | HealthSolutions Revamp | Bug |  | Rejected | High | No of products in cart not updating | Hamza Zubair | Shaji Ul Haq | 10/13/2020 9:05 | Android | [5 empty] | 0 | 0 | 0 | 9/23/2020 10:47 | 10/13/2020 9:05 | Hamza Zubair |  |  |  |  | No | After adding products in cart, the no of products in "Cart" icon at the top right corner are not displaying but the item is added in Cart
888528 | HealthSolutions Revamp | Bug |  | Closed | Normal | Delivery charges not showing | Shahzaib Idrees | Shaji Ul Haq | 10/15/2020 14:44 | Android |  | 9/23/2020 |  |  |  | 0 | 0 | 0 | 9/23/2020 10:39 | 10/15/2020 14:44 | Hamza Zubair |  | 16.png |  |  | No | In "Blood Request" section delivery charges not showing, should be display delivery charges.
888524 | HealthSolutions Revamp | Bug |  | Closed | High | Map location in Blood Request section | Shahzaib Idrees | Shaji Ul Haq | 10/22/2020 10:06 | Android |  | 9/23/2020 |  |  |  | 0 | 0 | 0 | 9/23/2020 10:20 | 10/22/2020 10:06 | Hamza Zubair |  |  |  |  | No | In "Blood" section go on "Request Blood" section, and search any location and click selected location but map location automatically generate different location.
888514 | HealthSolutions Revamp | Bug |  | Closed | High | Location not updating automatically | Hamza Zubair | Shaji Ul Haq | 10/22/2020 11:19 | Android |  | 9/23/2020 |  |  |  | 0 | 0 | 0 | 9/23/2020 8:59 | 10/22/2020 11:19 | Hamza Zubair |  |  |  |  | No | On selecting the location in any of the segment, on clicking on the location text box, when map screen opens than it isn't automatically redirecting the user to his current location but instead the user needs to tap on the location icon to switch to his current location.
888505 | HealthSolutions Revamp | Bug |  | Closed | High | Unexpected error after logging in | Hamza Zubair | Shaji Ul Haq | 10/20/2020 15:20 | Android |  | 9/23/2020 |  |  |  | 0 | 0 | 0 | 9/23/2020 8:49 | 10/20/2020 15:20 | Hamza Zubair |  |  |  |  | No | Getting an unexpected error message on logging in.
888504 | HealthSolutions Revamp | Bug |  | Closed | High | Getting unexpected error after signing up | Hamza Zubair | Shaji Ul Haq | 10/20/2020 15:14 | Android |  | 9/23/2020 |  |  |  | 0 | 0 | 0 | 9/23/2020 8:46 | 10/20/2020 15:14 | Hamza Zubair |  |  |  |  | No | After signing up, when the user is moved to the home screen than getting an unexpected error message.
888502 | HealthSolutions Revamp | Bug |  | Closed | High | First name field blank in sign up | Hamza Zubair | Shaji Ul Haq | 10/20/2020 15:19 | Android |  | 9/23/2020 |  |  |  | 0 | 0 | 0 | 9/23/2020 8:34 | 10/20/2020 15:19 | Hamza Zubair |  |  |  |  | No | If the "First Name" field is blank than after signing up by filling all the fields except "First Name", getting an unexpected error but instead a message should be displayed as, "All fields are mandatory"
888496 | HealthSolutions Revamp | Bug |  | New | Low | Phone number and Email validation message text | Hamza Zubair | Shaji Ul Haq | 9/23/2020 8:14 | Android |  | 9/23/2020 |  |  |  | 0 | 0 | 0 | 9/23/2020 8:14 | [6 empty] | No | If a user uses already registered number or email for sign up, than a message is displayed as, "email has already been taken" & "phone number has already been taken". "E" should be in upper case in "Email" and "P" should also be in upper case in "Phone".
888492 | HealthSolutions Revamp | Bug |  | New | Normal | Sign up form fields limitation | Hamza Zubair | Shaji Ul Haq | 10/20/2020 15:16 | Android |  | 9/23/2020 |  |  |  | 0 | 0 | 0 | 9/23/2020 7:47 |  | Hamza Zubair |  |  |  |  | No | Insert the data limitation validation in all the sign up form fields as required.
888491 | HealthSolutions Revamp | Feature |  | New | Low | Sign up text box fields auto validation | Hamza Zubair | Shaji Ul Haq | 9/23/2020 7:40 | Android |  | 9/23/2020 |  |  |  | 0 | 0 | 0 | 9/23/2020 7:40 | [6 empty] | No | On entering data into the sign up text boxes, if the entered data is valid than a "Green tick" should be displayed on that field but if the entered data is invalid than a "Red Cross" should be displayed on that field. For e.g If the password and confirm password fields do not match than a small "Red Cross" should be displayed on that text box to let the user know that the entered data is invalid. Currently if any field is invalid than the user gets to know it after submitting the form which is sometimes irritating for users.
888490 | HealthSolutions Revamp | Bug |  | Closed | Low | Width of sign up text boxes | Hamza Zubair | Shaji Ul Haq | 10/15/2020 13:55 | Android |  | 9/23/2020 |  |  |  | 0 | 0 | 0 | 9/23/2020 7:29 | 10/15/2020 13:55 | Hamza Zubair |  |  |  |  | No | Decrease the width of the "Sign up" page text boxes in a way that it should not collide with the edges of the phone's screen.
888487 | HealthSolutions Revamp | Bug |  | Closed | Low | Terms & conditions check box position | Hamza Zubair | Shaji Ul Haq | 10/15/2020 13:54 | Android |  | 9/23/2020 |  |  |  | 0 | 0 | 0 | 9/23/2020 7:22 | 10/15/2020 13:54 | Hamza Zubair |  |  |  |  | No | The position of the "Terms & Conditions agreement" check box is not aligned with the text on sign up screen.
888344 | HealthSolutions Revamp | Feature |  | New | High | Add wallet in payment methods | Hamza Zubair | Shaji Ul Haq | 9/22/2020 6:03 |  |  | 9/22/2020 |  |  |  | 0 | 0 | 0 | 9/22/2020 6:03 | [6 empty] | No | Add "Wallet" option in payment methods. The user should be able to use wallet amount for transaction with in all the segments.
888276 | HealthSolutions Revamp | Feature |  | Closed | High | App features and instructions screens on launching the app first time after installation | Hamza Zubair | Shaji Ul Haq | 10/22/2020 14:21 |  |  | 9/21/2020 |  |  |  | 0 | 0 | 0 | 9/21/2020 11:59 | 10/22/2020 14:21 | Hamza Zubair |  |  |  |  | No | When the app is installed for the first time, than after launching the app, a list of intro screens should be opened displaying the app features or instructions about the app. The user have two options on this screen, either he can view all the screens by clicking on "Next" or can skip that into by clicking on "Skip" button.
887857 | HealthSolutions Revamp | Task |  | New | High | Emails not receiving | Hamza Zubair | Muhammad Faizan Raza | 9/18/2020 6:31 |  |  | 9/18/2020 |  |  |  | 0 | 0 | 0 | 9/18/2020 6:31 | [6 empty] | No | Generate the emails to support and user on sign up, change password, forget password and on placing order. Currently not getting any email
887855 | HealthSolutions Revamp | Feature |  | Closed | High | Home screen design change | Hamza Zubair | Shaji Ul Haq | 10/15/2020 13:54 | Android |  | 9/18/2020 |  |  |  | 0 | 0 | 0 | 9/18/2020 6:23 | 10/15/2020 13:54 | Hamza Zubair |  |  |  |  | No | Change the home screen design to half scrollable wheel.
887811 | HealthSolutions Revamp | Bug |  | Closed | High | Recommended key is not working in "Doctors" API | Hamza Zubair | Muhammad Faizan Raza | 10/22/2020 11:17 | API |  | 9/18/2020 |  |  |  | 0 | 0 | 0 | 9/18/2020 5:21 | 10/22/2020 11:17 | Hamza Zubair |  |  |  |  | No
887693 | HealthSolutions Revamp | Bug |  | New | High | Review rating | Hamza Zubair | Muhammad Faizan Raza | 9/17/2020 11:33 | API |  | 9/17/2020 |  |  |  | 0 | 0 | 0 | 9/17/2020 11:33 | [6 empty] | No | Round off doctor's rating to one decimal place.
887618 | HealthSolutions Revamp | Bug |  | Closed | Normal | Brands API is not in collection | Hamza Zubair | Muhammad Faizan Raza | 10/14/2020 14:24 | API |  | 9/17/2020 |  |  |  | 0 | 0 | 0 | 9/17/2020 7:37 | 10/14/2020 14:24 | Hamza Zubair |  |  |  |  | No
887604 | HealthSolutions Revamp | Bug |  | Closed | High | Mark Default Address API is not working | Hamza Zubair | Muhammad Faizan Raza | 10/14/2020 14:23 | API |  | 9/17/2020 |  |  |  | 0 | 0 | 0 | 9/17/2020 7:03 | 10/14/2020 14:23 | Hamza Zubair |  |  |  |  | No
887601 | HealthSolutions Revamp | Bug |  | Closed | High | Appointment booking with out time slot | Hamza Zubair | Muhammad Faizan Raza | 10/14/2020 14:23 | API |  | 9/17/2020 |  |  |  | 0 | 0 | 0 | 9/17/2020 6:10 | 10/14/2020 14:23 | Hamza Zubair |  |  |  |  | No | The user is able to book appointment with out time slots.
887551 | HealthSolutions Revamp | Feature |  | Closed | Normal | Two images in "Speciality" API | Hamza Zubair | Muhammad Faizan Raza | 10/14/2020 14:22 | API |  | 9/16/2020 |  |  |  | 0 | 0 | 0 | 9/16/2020 12:50 | 10/14/2020 14:22 | Hamza Zubair |  |  |  |  | No | There should be two images in API for each speciality icon. One is for selected icon and the other for un-selected.
887548 | HealthSolutions Revamp | Task |  | Closed | High | Discounted Amount is showing as Total Amount in "Book Appointment" API | Hamza Zubair | Muhammad Faizan Raza | 10/14/2020 14:21 | API |  | 9/16/2020 |  |  |  | 0 | 0 | 0 | 9/16/2020 12:01 | 10/14/2020 14:21 | Hamza Zubair |  |  |  |  | No | In "Book appointment" API, the discounted amount is showing as "Total amount" but instead "Total Amount" should be "Amount-Discounted amount"
887544 | HealthSolutions Revamp | Bug |  | Closed | High | Time slot API is empty | Hamza Zubair | Muhammad Faizan Raza | 10/14/2020 14:21 | API |  | 9/16/2020 |  |  |  | 0 | 0 | 0 | 9/16/2020 11:44 | 10/14/2020 14:21 | Hamza Zubair |  |  |  |  | No | Doctor time slot API is empty. Not getting doctor's available time slots in this API but instead getting doctor's "longitude" and "speciality_id".
887536 | HealthSolutions Revamp | Feature |  | New | Normal | Login with email or phone number | Hamza Zubair | Shaji Ul Haq | 10/29/2020 11:19 | API |  | 9/16/2020 |  |  |  | 0 | 0 | 0 | 9/16/2020 10:35 |  | Hamza Zubair |  |  |  |  | No | The user should be able to login with both email and phone number. Add "Phone Number" key in "Login API"