## Sheet1
HS Admin Panel Testing
Sr. no | Bug Description | Priority | Reported by | Assigned to | Status | Comments (If any)
1 | The settings button at the top right corner is not working. | P2 | Engr. M. Hamza Zubair | Arshad Iqbal | completed
2 | The user profile is not opening after clicking on "Profile button" . Steps: 1)Click on the image icon at the top right corner then click on profile button. | P2 | Engr. M. Hamza Zubair | Arshad Iqbal | completed
3 | The menu list is not minimizing after clicking on menu bar. Steps: 1)Go to any child screen from the menu list than click on the menu bar, it is not minimizing. | P3 | Engr. M. Hamza Zubair | Arshad Iqbal | pending
4 | The ambulance request screen is not opening | Pending | Engr. M. Hamza Zubair | Arshad Iqbal | pending
5 | Add a sorting filter in all the columns for sorting the Blood requests in ascending and descending order in "Blood Requests" | P2 | Engr. M. Hamza Zubair | Arshad Iqbal | completed
6 | The location is not showing in "Blood Requests". The location link should be displayed and after clicking on it the location should be displayed and opened through Google Maps. | P1 | Engr. M. Hamza Zubair | Arshad Iqbal | pending | App issue
7 | After updating the "Rider Details" in "Blood Requets", the details are saved but showing an error "404 Page Not Found" after updating the details. Steps: 1)Click on the view (i) button in action column | P2 | Engr. M. Hamza Zubair | Arshad Iqbal | completed
8 | The "Donor Name" is not showing in "Blood Donation Requests" Hint: The name of the app account holder should be displayed in this field. | P2 | Engr. M. Hamza Zubair | Arshad Iqbal | completed
9 | The status is not updating in "Blood Donation Request". Getting an error "404 Page Not Found" after updating status | P1 | Engr. M. Hamza Zubair | Arshad Iqbal | completed
10 | The latest blood donate requests are not showing on the top of the list. The latest requests should be displayed on the top. | P2 | Engr. M. Hamza Zubair | Arshad Iqbal | completed
11 | The Blood Donate Request is deleting successfully but getting an error message, "404 Page not found" after deletion. | P3 | Engr. M. Hamza Zubair | Arshad Iqbal | completed
12 | In chemist section change the name "Orders" to "Order by search" | P3 | Engr. M. Hamza Zubair | Arshad Iqbal
13 | Add a sorting filter for sorting the Order List in ascending and descending order in "Chemist" orders | P2 | Engr. M. Hamza Zubair | Arshad Iqbal
14 | The wrong order time is displaying in "Created At" field in "Order by search" | P2 | Engr. M. Hamza Zubair | Arshad Iqbal
15 | The "Order by prescription" screen is opening in a different view | P2 | Engr. M. Hamza Zubair | Arshad Iqbal
16 | The wrong order time is displaying in "Created At" filed in "Order by prescription" section | P2 | Engr. M. Hamza Zubair | Arshad Iqbal
17 | Add an option to upload medicine image in "Add Medicines" section | P1 | Engr. M. Hamza Zubair | Arshad Iqbal
18 | After adding a test in Diagnostics from the "Add Test" section, a message is displaying that "Test added successfully" but it is not added and displaying in the "Test List" | P1 | Engr. M. Hamza Zubair | Arshad Iqbal
19 | After adding a report from "Add reports" section, a message is displaying "Report added" but on app level, the uploaded report from the panel is not displaying. | P1 | Engr. M. Hamza Zubair | Arshad Iqbal
20 | The Equirments section is not completed | P1 | Engr. M. Hamza Zubair | Arshad Iqbal
21 | Unable to edit the user's info in "App users" section. Getting an error message, "An Error Was Encountered" after clicking on edit button. | P1 | Engr. M. Hamza Zubair | Arshad Iqbal
22 | The wallet amount is not updating. After clicking on save, a message is displaying "Mazrat" Hint: Click on the "$" button in "Action" field to update wallet amount | P1 | Engr. M. Hamza Zubair | Arshad Iqbal
23 | Unable to change the user's status as "Active" or "Inactive" | P1 | Engr. M. Hamza Zubair | Arshad Iqbal
24 | After deleting any app user, the account is not deleting from both databases i.e assad_qb and assad_hsa. | P1 | Engr. M. Hamza Zubair | Arshad Iqbal
25 | There is no option to add new rider in "Riders" section | P1 | Engr. M. Hamza Zubair | Arshad Iqbal
26 | After creating a new user role from "User_Role" section inside "System Users", the newly created user is showing in the User roles view section but on viewing any particular user role, the fields that were marked during the time of creating a role are not marked but instead all the fields are marked and also on viewing any of the user role, the user role "admin" is opening. | P1 | Engr. M. Hamza Zubair | Arshad Iqbal
27 | Unable to edit a system user in "View users" section inside "System Users". On editing getting a message, "This page isn’t workinghealthsolutions.com.pk is currently unable to handle this request. HTTP ERROR 500" | P1 | Engr. M. Hamza Zubair | Arshad Iqbal
28 | The id, name, email, pass, contact no, address fields are not displaying in "Users View" inside "System Users" | P1 | Engr. M. Hamza Zubair | Arshad Iqbal
29 | The user role is not deleting in "User role view" section. After deleting a message is displaying as "404 Page Not Found" and on the "User Role view" screen a message is displaying "Deleted successfully" but it's not deleted. | P1 | Engr. M. Hamza Zubair | Arshad Iqbal
30 | After deleting a notification from "Notifications" section the Add notification screen is opening. It shouldn't be opened instead it should go back to notifications list screen. | P3 | Engr. M. Hamza Zubair | Arshad Iqbal
31 | Change the default account image with Health Solutions logo image | P3 | Engr. M. Hamza Zubair | Arshad Iqbal
32 | The complete info is not showing in "Blood Requests" exported pdf file in "Accounts" section. | P1 | Engr. M. Hamza Zubair | Arshad Iqbal
33 | There is no option to edit the details in "Order by prescription" inside chemist section. | P1 | Engr. M. Hamza Zubair | Arshad Iqbal
34 | There should be an option to delete entry in "Diagnostics Test Request" list | P2 | Engr. M. Hamza Zubair | Arshad Iqbal
35 | On doing order by prescription from the app, the image is not showing in the "Diagnostics Requests list". If the user places an order by prescription than the image link should be displayed in the "Test Name" column inside "Diagnostic Test" | P1 | Engr. M. Hamza Zubair | Arshad Iqbal
36 | The fields "Name", "Rate", "Reporting Day", "Received Amount", "Delivery Charges", "Delivery By" are not displaying in "Diagnostics" section inside "Account" HINT: In the other sections, these fileds are updated in "Accounts" by updating the details in the "Requests" section but for "Diagnostics" the above mentioned fields are not present in the "Diagnostics Request" so we can't update these fields that's why these fields cannot be updated in "Diagnostic Test Report" in "Accounts" | P1 | Engr. M. Hamza Zubair | Arshad Iqbal
37 | The format of the whole Admin panel sections should be same. For e.g If the latest entries are displaying on the top than it should be same for all the sections and vice versa. It should not be the case that in some section latest entries are showing on the top and in some after sorting coming on the top so the flow through out the panel should be same. | P1 | Engr. M. Hamza Zubair | Arshad Iqbal