## Wilgo User
S.no | Bugs/Enhancement | Type | Priority | Status
1 | Spelling mistake in "Current Location" on pick up location page and in place holder as well, after selecting "Current location" | Bug | P2
2 | On selecting "Current", "Work" or "Home" locations from pick up page, the complete location name should be displayed below and on clicking it the user should be moved to that location on the map. | Bug | P1
3 | No notification is showing at the user's end once the driver accepts the ride request + user is not receiving any notifications when driver is proceeding with the ride request from start till end of ride. (The notifications should be received at the user's end at each and every step of the ride as proceeded by the driver. (HAPPENING SOMETIMES) | Bug | P0
4 | Nothing is showing at the user's end during complete ride cycle about the ride request progress once the ride request is accepted and completed by the driver. (HAPPENING SOMETIMES) | Bug | P0
5 | Push notifications are not receiving | Bug | P1
6 | Ride cancellation reason at the time of cancelling the ride from the driver's end is not displaying at the user's end. (Hint the reason should be displayed in the same ride cancellation pop up in the format, "Ride cancelled by driver + due to + reason)" | Bug | P2
7 | There should be an option for user to go back from "Select car class" screen if he has mistakenly selected the wrong ride type, "Private" or "Shared" and wants to select it again. | Bug | P2
8 | Most of the fields are static on "My trip" details page. | Bug | P1
9 | Notifications are static | Bug | P1
10 | On "My trips" page, the trip list should be updated on real time. Currently it's updating once the user closed and re-opens the app. | Bug | P2
11 | If there is no listing available on "My trips" page than a text, "No Record(s) Found!" should be displayed in that section. | Bug | P3
12 | Static data is showing for all the fields on "My trips" & "Trip Details" pages. | Bug | P1
13 | Once the ride is completed by the driver, sometimes ride completed pop up is not showing at user's end and user is stucked at the ride details screen. | Bug | P1
14 | The user should also be able to select or change pick up and drop off locations on clicking the locations text box on the top. Currently user is only able to do that on clicking the cross at the top right. | Enhancement | P3
15 | There should be a back button on the top left corner of "Add card" screen. | Bug | P3
16 | Unable to select card from "My payment info" screen under "Settings" | Bug | P1
17 | Some times the color scheme is vanishing on using the app. This issue is coming for whole app. | Bug | P1
18 | Keypad "Next" & "Return" buttons are not working throughout the app for switching the fields | Bug | P2
19 | App stucks if a long number is added and user saves the profile on "User Edit Profile" screen. | Bug | P2
20 | Unable to update user's profile picture on Edit Profile screen | Bug | P1
21 | "Change password" not working. | Bug | P1
22 | The time restriction pop up should not restrict the user to schedule a ride, if he's booking the ride for the next date or month. | Bug | P2
23 | Messages not sending to driver for "Shared" rides during a ride. | Bug | P1
24 | "Yes Cancel" button on confirmation pop up not working on cancelling the schedule ride request. | Bug | P2
25 | There should be a location Re-centre button available on the home screen, which on click should take the user to his current location. | Bug | P2
26 | The disable person's availablility icon is showing to driver when ride request is received but these is no option for its selection "Yes" or "No" at the time of making ride request from user. | Bug | P1
27 | For all the "Saved" locations the name of that location should be displayed through out the app instead of shoowing "Current", "Home" etc | Bug | P1
28 | On signing up a new user, by default, the user's rating should be "0" but currently it's showing "3 stars" | Bug | P2
29
Wilgo User (iOS app) Module: Ride Booking flow
Testing type: Exploratory testing
Test Run Information:
Tester Name: Muhammad Hamza Zubair
Date(s) of Test: 10/3/2022
Prerequisites for this test: 1)Your device should be net connected
2)Wilgo user app should be installed.

## Wilgo Driver
S.no | Bugs/Enhancement | Type | Priority | Status
1 | There should be a location Re-centre button available on the home screen, which on click should take the driver to his current location. | Bug | P2
2 | On the login screen, the user name should be changed to "Email" as it is taking email as input. | Bug | P2
3 | Spelling mistakes in error messages, if the user enters wrong email or password or keep both fields blank. | Bug | P3
4 | The user is able to get the reset code on clicking "Reset code" before the timer stops but instead he shouldn't be allowed to do so as long as the timer is not complete. | Bug | P2
5 | If the user proceed by entering wrong verification code on "OTP" code page than no message is prompting to user. A message should be prompt as "Invalid OTP" to let the user know that he has entered in correct OTP. | Bug | P3
6 | When a ride request is received to driver, than both location names should be displayed for "Pick up" and "Drop off" instead of showing label names in pick up location like "Current", "Work" or "Home" etc | Bug | P1
7 | The driver is getting ride request and the user is able to send the ride request when both are currently in ride. (If the driver is already in a ride, then he shouldn't receive any ride requests and in the same way if any user is already in ride than he shouldn't be allowed to make a ride request. | Bug | P1
8 | The driver is still receiving the ride requests if he's offline. | Bug | P1
9 | "Messages" option is not funtional yet and messages are not receiving at the user's end. (Happening sometimes) | Bug | P1
10 | A small red dot should be displayed above "Messages" option at driver's end, if a message is sent by the user. | Bug | P3
11 | "Car icon" is dropping on opening the app from background. | Bug | P2
12 | Getting "Private" rides on "Shared" driver and vice versa. | Bug | P1
13 | The driver should receive ride requests according to customer's preference. Currently if there is SUV driver, he's getting the requests from "VAN" requesters and vice versa. | Bug | P1
14 | Complete data is not showing on "My Trips" details page + Wrong ride status is showing. | Bug | P1
15 | Notifications are static | Bug | P1
16 | Change "Call driver" text to just "Call" on "Schedule Trips Details" screen, as it's driver himself. | Bug | P2
17 | On "My trips" page, the trip list should be updated on real time. Currently it's updating once the user closed and re-opens the app. | Bug | P2
18 | "Change password" not working. | Bug | P1
19 | User's profile not updating | Bug | P1
20 | Rating & Reviews are static in driver's profile | Bug | P1
21 | Messages not sending to user for "Shared" rides during a ride. | Bug | P1
22 | For shared rides after clicking location re-center icon, the driver is moved to his current location but no marker is showing on the map. A car icon should be displayed on driver's current location. | Bug | P3
23 | The ride request accept timer that shows to driver should still be continued if the app is in background | Bug | P1
24 | For all the "Saved" locations the name of that location should be displayed through out the app instead of showing "Current", "Home" etc | Bug | P1
Wilgo Driver (Android app) Module: Ride booking flow
Testing type: Exploratory testing
Test Run Information:
Tester Name: Muhammad Hamza Zubair
Date(s) of Test: 10/3/2022
Prerequisites for this test: 1)Your device should be net connected
2)Wilgo driver app should be installed.